Volunteering Rewards App — Member Task Allocation (Revised)

Project: Volunteering Rewards App   Date: May 10, 2026   Version: 2.0 — Phase 1 Simplified (No merchants/cashiers, vibe coding approach)   Team: Xon, Nurain, Vivian, Grace   Total Tasks: 62 core tasks + 17 frontend/gap tasks

Working Model: Vibe Coding

This project follows a vibe coding approach:

I (Claude) generate all application code based on workflow descriptions

Team members test on real devices (Expo Go for mobile, browser for web)

Team reports issues and bugs back to me for iteration

Everyone participates in every phase — testing what's built, finding edge cases, and giving feedback

This is NOT a traditional Design → Integration → Testing waterfall. Each workflow is built end-to-end:

We build it → they test it → we fix it → they approve it

How Tasks Work in Practice

Each task listed below is test-driven. For example, AUTH-03 · Mobile login screen means:

I generate the login screen code

Xon/Nurain test it on Expo Go (correct email → logged in, wrong password → error shown)

They report any issues

I fix and regenerate

Task marked complete when it passes real-device testing

Role Summary

| Member | Primary Workflow Ownership | Testing Device |
| --- | --- | --- |
| Xon | Infrastructure + All workflows (code generation coordinator) | Expo Go + Web |
| Nurain | Workflow A — Auth & User Management | Expo Go |
| Vivian | Workflow B — Events & QR Scanning | Expo Go |
| Grace | Workflow C — Rewards & Redemption + Frontend web portals | Expo Go + Web |

Shared Responsibilities (Everyone)

| Responsibility | Frequency |
| --- | --- |
| Daily standup — what was tested, what broke, what's next | Every FYP day |
| Test new features on personal device | As features are generated |
| Report bugs with steps to reproduce | As found |
| Update Git branches with tested code | After each working session |
| Contribute to presentation slides | Sprint 5 |

Infrastructure & Setup — Xon (Lead)

These are the foundation tasks. Must be completed before workflow tasks begin.

| ID | Task | Details | Duration | Status |
| --- | --- | --- | --- | --- |
| INF-01 | Backend project scaffolding | Set up Express.js project structure (routes/, controllers/, services/, middleware/, config/). Install dependencies: express, pg, bcrypt, jsonwebtoken, joi, cors, dotenv, nodemon. | Sprint 1 | ⏳ |
| INF-02 | Database connection | Set up PostgreSQL connection pool via pg package. Create config/database.js. Verify with GET /api/health endpoint. | Sprint 1 | ⏳ |
| INF-03 | Migration runner | Set up migration system (e.g., node-pg-migrate or raw SQL files). Create initial migration for all 12 core tables following DATABASE_TABLES_v2.md. | Sprint 1 | ⏳ |
| INF-04 | Seed data script | Create seed script with: 3 roles, 2 test volunteers, 1 organizer, 1 admin, 1 organization (approved), 3 events, 5 coupons. Used by all members for testing. | Sprint 1 | ⏳ |
| INF-05 | Git branching setup | Maintain branches: main, xon, nurain, vivian, grace. Ensure each member can pull latest generated code and push tested changes. | Sprint 1 | ⏳ |
| INF-06 | API error handler | Global error handler middleware. Consistent JSON error format: { error: { code, message, details? } }. Covers validation errors, auth errors, not found, server errors. | Sprint 1 | ⏳ |
| INF-07 | API consistency audit | Review all API routes for consistent error format, correct status codes, and proper response envelopes. | Sprint 5 | ⏳ |

Workflow A: Auth & User Management — Nurain (Owner)

Backend routes + mobile screens for registration, login, user profile, organization registration.

Backend Tasks

| ID | Task | Details | API Endpoints | Duration |
| --- | --- | --- | --- | --- |
| AUTH-01 | Registration API | User registration for volunteers and organizers. Validate email uniqueness, hash password with bcrypt, return JWT. | POST /api/auth/register | Sprint 1 |
| AUTH-02 | Login API | Authenticate with email + password. Return access token + refresh token. Same error for wrong email or password (no user enumeration). | POST /api/auth/login | Sprint 1 |
| AUTH-03 | JWT middleware | Verify Bearer token, decode payload, attach req.user. Handle expired token (401), malformed token (401). | Middleware | Sprint 1 |
| AUTH-04 | Role guard middleware | Check req.user.role against required role(s). Return 403 if insufficient. | Middleware | Sprint 1 |
| AUTH-05 | Token refresh API | Issue new access token from valid refresh token. Rotate refresh token (old one invalidated). | POST /api/auth/refresh | Sprint 1 |
| AUTH-06 | User profile API | Get current user profile, update profile (name, phone, profile image URL). | GET /api/auth/me, PUT /api/users/:id | Sprint 1 |
| AUTH-07 | Admin user management | List all users, view user details, suspend/reactivate accounts, reset passwords. Admin only. | GET /api/users, PUT /api/users/:id/status | Sprint 2 |
| AUTH-08 | Organization registration | Create organization with name, UEN, contact info, document upload. Default status: pending. | POST /api/organizations | Sprint 2 |
| AUTH-09 | Organization approval | Admin reviews org documents → approve or reject. Sets approval_status and approved_by. | PUT /api/organizations/:id/approve | Sprint 2 |
| AUTH-10 | Rate limiter | Apply rate limiting to auth endpoints (e.g., 5 login attempts per minute per IP). | Middleware | Sprint 1 |

Mobile Screens

| ID | Task | Details | Dependency |
| --- | --- | --- | --- |
| AUTH-M01 | Registration screen | Volunteer registration form: name, email, password, phone. Field validation. Success → navigate to home. Error states shown inline. | AUTH-01 |
| AUTH-M02 | Login screen | Email + password fields. Forgot password link (placeholder). JWT stored in secure storage. | AUTH-02 |
| AUTH-M03 | Profile screen | Display user name, email, points, QR code. Edit profile button. | AUTH-06 |
| AUTH-M04 | QR code display screen | Show volunteer's unique QR code (UUID-based). Large enough for organizer to scan. Refresh button. | AUTH-06 |

Testing Checklist (Nurain)

[ ] Register volunteer → created, logged in, see home screen

[ ] Register duplicate email → 409 error shown

[ ] Register with missing fields → validation errors shown per field

[ ] Login correct credentials → JWT stored, redirected to home

[ ] Login wrong password → error message (no hint if email exists)

[ ] Login deactivated account → 403 shown

[ ] Access protected route without token → 401

[ ] Access organizer route as volunteer → 403

[ ] Refresh token works, old token rejected after rotation

[ ] QR code displays correctly and is scannable

[ ] Organization registration with document upload works

[ ] Admin can approve/reject organization

[ ] Admin can suspend user account

Workflow B: Events & QR Scanning — Vivian (Owner)

Backend routes + mobile screens for events, registration, QR attendance, feedback, Q&A.

Backend Tasks

| ID | Task | Details | API Endpoints | Duration |
| --- | --- | --- | --- | --- |
| EVT-01 | Event CRUD | Create, read, update, cancel events. Organizer can only manage own events. Status lifecycle: upcoming → ongoing → completed → cancelled. | GET/POST /api/events, GET/PUT/DELETE /api/events/:id | Sprint 2 |
| EVT-02 | Event search & filter | Search by title/description. Filter by category, date range, location. Pagination (default 20 per page). | GET /api/events?search=&category=&date_from=&date_to=&page= | Sprint 2 |
| EVT-03 | Event registration | Volunteer joins event (creates event_registrations row). Check capacity, prevent double-registration. Cancel registration. | POST /api/events/:id/register, DELETE /api/events/:id/register | Sprint 2 |
| EVT-04 | QR scan endpoint | Organizer scans volunteer QR → records attendance in attendance_logs. Two scan types: check_in and points_award. Prevents duplicate scans. | POST /api/attendance/scan | Sprint 3 |
| EVT-05 | Attendance list | Organizer views attendance list for their event. Shows who checked in, method, timestamp. | GET /api/events/:id/attendance | Sprint 3 |
| EVT-06 | Feedback submission | Volunteer submits rating (1-5) + comment after event. One feedback per event per volunteer. | POST /api/events/:id/feedback | Sprint 3 |
| EVT-07 | Feedback summary | Organizer views aggregated feedback scores and comments for their event. | GET /api/events/:id/feedback | Sprint 3 |
| EVT-08 | Event Q&A | Volunteer asks question. Organizer answers. Questions published by default. | POST /api/events/:id/questions, PUT /api/qna/:id/answer, GET /api/events/:id/qna | Sprint 3 |
| EVT-09 | Favorites | Volunteer favorites an event or coupon. List user's favorites. Remove favorite. | POST/DELETE /api/favorites, GET /api/favorites | Sprint 3 |
| EVT-10 | Points awarding | On scan_type = 'points_award', add events.points_value to users.points. Record in attendance_logs.points_awarded. | Part of EVT-04 logic | Sprint 3 |

Mobile Screens

| ID | Task | Details | Dependency |
| --- | --- | --- | --- |
| EVT-M01 | Event browse screen | List of upcoming events. Search bar. Category filter chips. Pull-to-refresh. Loading/empty/error states. | EVT-02 |
| EVT-M02 | Event detail screen | Title, description, date/time, location, capacity, points value. Join/Cancel button. Favorite toggle. | EVT-01, EVT-03 |
| EVT-M03 | QR scanner screen (Organizer) | Camera viewfinder. Scans volunteer's QR code. Two buttons: Check In and Award Points. Success/error overlay. | EVT-04 |
| EVT-M04 | Feedback form screen | Star rating (1-5) + comment text area. Submit button. Success confirmation. | EVT-06 |
| EVT-M05 | Organizer event management | List own events with status. Create/edit event form. View attendance per event. | EVT-01, EVT-05 |
| EVT-M06 | Q&A screen | List of questions. Ask question form. Organizer sees answer button. | EVT-08 |

Testing Checklist (Vivian)

[ ] Create event as organizer → appears in browse list

[ ] Create event as volunteer → 403

[ ] Browse events with search/filter → correct results

[ ] Join event → registration confirmed

[ ] Join full event → capacity error

[ ] Join same event twice → duplicate registration prevented

[ ] Cancel registration → removed from list

[ ] Organizer scans volunteer QR → check-in recorded

[ ] Duplicate scan → prevented (UNIQUE constraint)

[ ] Points awarded on points_award scan

[ ] Submit feedback → rating recorded

[ ] Duplicate feedback → prevented

[ ] Ask question, organizer answers → displayed correctly

[ ] Favorite an event → appears in favorites list

[ ] Organizer views attendance list → correct data

Workflow C: Rewards & Redemption — Grace (Owner)

Backend routes + mobile screens for coupons, redemption, PIN generation, admin verification.

Backend Tasks

| ID | Task | Details | API Endpoints | Duration |
| --- | --- | --- | --- | --- |
| REW-01 | Coupon CRUD (Admin) | Create, read, update coupons. Fields: title, description, pointsrequired, quantity, expirydate, image_url. Status: active/inactive/depleted. | GET/POST /api/coupons, GET/PUT /api/coupons/:id | Sprint 3 |
| REW-02 | Coupon browse (Volunteer) | List active coupons with quantity > 0 and not expired. Filter by favorites. | GET /api/coupons?favorites=true | Sprint 3 |
| REW-03 | Redemption API | Volunteer redeems points for coupon. Check: sufficient points, coupon active, quantity > 0, not expired. Deduct points, decrement quantity, generate PIN, create user_coupons row. | POST /api/redeem | Sprint 3 |
| REW-04 | PIN generation | crypto.randomInt(100000, 999999).toString(). Must be unique (UNIQUE constraint on user_coupons.pin). Retry if collision (extremely rare). | Part of REW-03 | Sprint 3 |
| REW-05 | PIN verification (Admin) | Admin enters 6-digit PIN → verify exists, unused, not expired. Return coupon title and volunteer name on success. Mark as used. | POST /api/verify-pin | Sprint 4 |
| REW-06 | Redemption audit log | Log all redemption actions: redeemed, used, expired. Record who performed the action and IP address. | Part of REW-03, REW-05 | Sprint 4 |
| REW-07 | Auto-expire coupons | Background check: mark user_coupons as expired if expiry_date passed and status is unused. Can be a simple migration or cron. | N/A | Sprint 4 |
| REW-08 | Coupon quantity enforcement | Decrement quantity atomically. Prevent overselling (race condition safe). Auto-set status to depleted when quantity reaches 0. | Part of REW-03 | Sprint 3 |

Mobile Screens

| ID | Task | Details | Dependency |
| --- | --- | --- | --- |
| REW-M01 | Coupon browse screen | Grid/list of available coupons. Card shows title, points cost, remaining quantity. Tap for detail. Favorite toggle. | REW-02 |
| REW-M02 | Coupon detail screen | Full description, image, points required, expiry date, quantity remaining. Redeem button. | REW-01 |
| REW-M03 | Redemption confirmation | Summary of coupon details. Confirm button. Shows points balance before/after. Cancel option. | REW-03 |
| REW-M04 | PIN display screen | Large 6-digit PIN display after successful redemption. "Copy PIN" button. Expiry date shown. Instructions: "Show this PIN to claim your reward." | REW-04 |

Web Screens

| ID | Task | Details | Dependency |
| --- | --- | --- | --- |
| REW-W01 | Admin coupon management | Coupon list with status filters (active/inactive/depleted). Create coupon form. Edit coupon. View redemption count. | REW-01 |
| REW-W02 | Admin PIN verification | Simple 6-digit input field. Submit button. Success: shows volunteer name + coupon name + "Mark as issued" confirmation. Failure: wrong PIN / already used / expired messages. | REW-05 |
| REW-W03 | Admin redemption audit | Table of all redemptions: volunteer, coupon, PIN (masked), status, date, admin who verified. Filterable. | REW-06 |

Testing Checklist (Grace)

[ ] Admin creates coupon → appears in volunteer browse

[ ] Volunteer redeems with sufficient points → PIN generated, points deducted, quantity decremented

[ ] Volunteer redeems with insufficient points → error shown

[ ] Redeem expired coupon → error shown

[ ] Redeem last available coupon → works, next request shows depleted

[ ] Two concurrent redemption requests → no overselling (race condition safe)

[ ] PIN is exactly 6 digits, numeric only

[ ] No two PINs are the same

[ ] Admin enters correct PIN → volunteer name + coupon name shown

[ ] Admin enters wrong PIN → error

[ ] Admin verifies already-used PIN → error

[ ] Verify expired PIN → error

[ ] Audit log shows all actions with timestamps and admin who performed them

[ ] Expired user coupons correctly marked as expired

[ ] Web portal coupon management works (create, edit, filter)

Frontend Foundation — Grace (Lead) + Everyone

Shared mobile app infrastructure and web app portals that span all workflows.

Mobile App (Expo)

| ID | Task | Details | Dependency |
| --- | --- | --- | --- |
| MOB-01 | Project setup | Initialize Expo project with file-based routing. Configure tabs layout (Home, Events, Rewards, Profile). Wire shared theme constants. | INF-01 |
| MOB-02 | Navigation structure | Set up stack navigators per tab. Deep-link support. Auth flow (login/register) vs main tabs. | MOB-01 |
| MOB-03 | Shared UI components | Button, Input, Card, Badge, LoadingSpinner, EmptyState, ErrorState, Toast. Reusable across all screens. | MOB-01 |
| MOB-04 | Home dashboard | Volunteer: points balance, upcoming events preview, quick QR code access. Organizer: event management shortcuts. | MOB-01 |
| MOB-05 | Event detail screen | Built from EVT-M02. Full event info, join/cancel, favorite, calendar add. | EVT-01, EVT-03 |
| MOB-06 | QR scanner screen | Built from EVT-M03. Camera scanner for organizers. QR display for volunteers. | EVT-04 |
| MOB-07 | Rewards screens | Built from REW-M01 to REW-M04. Browse, detail, confirm, PIN display. | REW-02, REW-03 |
| MOB-08 | Feedback & Q&A screens | Built from EVT-M04, EVT-M06. Rating, comments, questions list. | EVT-06, EVT-08 |

Web App (React)

| ID | Task | Details | Dependency |
| --- | --- | --- | --- |
| WEB-01 | Web project setup | Initialize React (Vite) project. Configure React Router. Sidebar + header layout. Role-based navigation. | INF-01 |
| WEB-02 | Shared web components | Reusable UI kit for web: DataTable, Form fields, Modal, Toast, Pagination. | WEB-01 |
| WEB-03 | Admin user management | User list table, search, suspend/reactivate action. User detail view. | AUTH-07 |
| WEB-04 | Organization approval | Pending orgs list, view documents, approve/reject buttons. History of approved orgs. | AUTH-09 |
| WEB-05 | Admin coupon management | Built from REW-W01. Coupon list, create/edit form. | REW-01 |
| WEB-06 | Admin PIN verification | Built from REW-W02. Simple PIN entry + verification result. | REW-05 |
| WEB-07 | Admin audit & reports | Built from REW-W03. Redemption log table, points activity summary. | REW-06 |

Gap Tasks

| ID | Task | Details | Who |
| --- | --- | --- | --- |
| GAP-01 | Loading/error state audit | Verify every screen handles: loading (spinner), empty (message), error (retry). Fix any blank-screen states. | Grace |
| GAP-02 | API integration audit | Confirm all mobile/web screens call live APIs, not mock data. Verify error propagation from backend to UI. | Xon |
| GAP-03 | Documentation | Keep docs/api.md current. Document every endpoint with request/response examples. | All |
| GAP-04 | Presentation slides | Capstone presentation: architecture, screenshots, demo script, Q&A prep. Start drafting in Sprint 4. | All |

Member Task Summary

Xon — Infrastructure + Code Generation Coordinator

| Category | Count | Details |
| --- | --- | --- |
| Infrastructure (INF) | 7 | Backend scaffolding, DB, migrations, seeds, Git, error handling, audit |
| Code generation | All | Generates all backend and frontend code via Claude |
| Total owned | 7 core + code gen for all |  |

Nurain — Workflow A: Auth & User Management

| Category | Count | Details |
| --- | --- | --- |
| Backend (AUTH) | 10 | Registration, login, JWT, roles, organizations, rate limiter |
| Mobile (AUTH-M) | 4 | Register, login, profile, QR display |
| Testing checkpoints | 14 | Functional test cases to verify |
| Total owned | 14 tasks + 14 test checks |  |

Vivian — Workflow B: Events & QR Scanning

| Category | Count | Details |
| --- | --- | --- |
| Backend (EVT) | 10 | Event CRUD, registration, QR scan, attendance, feedback, Q&A, favorites, points |
| Mobile (EVT-M) | 6 | Browse, detail, scanner, feedback, event mgmt, Q&A |
| Testing checkpoints | 17 | Functional test cases to verify |
| Total owned | 16 tasks + 17 test checks |  |

Grace — Workflow C: Rewards + Frontend Integration

| Category | Count | Details |
| --- | --- | --- |
| Backend (REW) | 8 | Coupon CRUD, redemption, PIN, verification, audit, expiry |
| Mobile (REW-M) | 4 | Browse, detail, confirm, PIN display |
| Web (REW-W) | 3 | Coupon mgmt, PIN verify, audit log |
| Frontend (MOB) | 8 | Project setup, navigation, UI kit, home, events, QR, rewards, feedback |
| Frontend (WEB) | 7 | Web setup, shared components, user mgmt, org approval, coupons, PIN, audit |
| Gap (GAP) | 4 | Error audit, integration audit, docs, presentation |
| Testing checkpoints | 15 | Functional test cases to verify |
| Total owned | 34 tasks + 15 test checks |  |

Complete Task Map

| ID | Task | Owner | Sprint |
| --- | --- | --- | --- |
| INF-01 | Backend project scaffolding | Xon | S1 |
| INF-02 | Database connection | Xon | S1 |
| INF-03 | Migration runner + all tables | Xon | S1 |
| INF-04 | Seed data script | Xon | S1 |
| INF-05 | Git branching setup | Xon | S1 |
| INF-06 | API error handler | Xon | S1 |
| INF-07 | API consistency audit | Xon | S5 |
| AUTH-01 | Registration API | Xon gen / Nurain test | S1 |
| AUTH-02 | Login API | Xon gen / Nurain test | S1 |
| AUTH-03 | JWT middleware | Xon gen / Nurain test | S1 |
| AUTH-04 | Role guard middleware | Xon gen / Nurain test | S1 |
| AUTH-05 | Token refresh API | Xon gen / Nurain test | S1 |
| AUTH-06 | User profile API | Xon gen / Nurain test | S1 |
| AUTH-07 | Admin user management | Xon gen / Nurain test | S2 |
| AUTH-08 | Organization registration | Xon gen / Nurain test | S2 |
| AUTH-09 | Organization approval | Xon gen / Nurain test | S2 |
| AUTH-10 | Rate limiter | Xon gen / Nurain test | S1 |
| AUTH-M01 | Registration screen | Xon gen / Nurain test | S2 |
| AUTH-M02 | Login screen | Xon gen / Nurain test | S2 |
| AUTH-M03 | Profile screen | Xon gen / Nurain test | S2 |
| AUTH-M04 | QR code display screen | Xon gen / Nurain test | S2 |
| EVT-01 | Event CRUD | Xon gen / Vivian test | S2 |
| EVT-02 | Event search & filter | Xon gen / Vivian test | S2 |
| EVT-03 | Event registration | Xon gen / Vivian test | S2 |
| EVT-04 | QR scan endpoint | Xon gen / Vivian test | S3 |
| EVT-05 | Attendance list | Xon gen / Vivian test | S3 |
| EVT-06 | Feedback submission | Xon gen / Vivian test | S3 |
| EVT-07 | Feedback summary | Xon gen / Vivian test | S3 |
| EVT-08 | Event Q&A | Xon gen / Vivian test | S3 |
| EVT-09 | Favorites | Xon gen / Vivian test | S3 |
| EVT-10 | Points awarding | Xon gen / Vivian test | S3 |
| EVT-M01 | Event browse screen | Xon gen / Vivian test | S2 |
| EVT-M02 | Event detail screen | Xon gen / Vivian test | S2 |
| EVT-M03 | QR scanner screen | Xon gen / Vivian test | S3 |
| EVT-M04 | Feedback form | Xon gen / Vivian test | S3 |
| EVT-M05 | Organizer event mgmt | Xon gen / Vivian test | S3 |
| EVT-M06 | Q&A screen | Xon gen / Vivian test | S3 |
| REW-01 | Coupon CRUD (Admin) | Xon gen / Grace test | S3 |
| REW-02 | Coupon browse (Volunteer) | Xon gen / Grace test | S3 |
| REW-03 | Redemption API | Xon gen / Grace test | S3 |
| REW-04 | PIN generation | Xon gen / Grace test | S3 |
| REW-05 | PIN verification (Admin) | Xon gen / Grace test | S4 |
| REW-06 | Redemption audit log | Xon gen / Grace test | S4 |
| REW-07 | Auto-expire coupons | Xon gen / Grace test | S4 |
| REW-08 | Coupon quantity enforcement | Xon gen / Grace test | S3 |
| REW-M01 | Coupon browse screen | Xon gen / Grace test | S3 |
| REW-M02 | Coupon detail screen | Xon gen / Grace test | S3 |
| REW-M03 | Redemption confirmation | Xon gen / Grace test | S3 |
| REW-M04 | PIN display screen | Xon gen / Grace test | S3 |
| REW-W01 | Admin coupon management | Xon gen / Grace test | S4 |
| REW-W02 | Admin PIN verification | Xon gen / Grace test | S4 |
| REW-W03 | Admin redemption audit | Xon gen / Grace test | S4 |
| MOB-01 | Mobile project setup | Xon gen / Grace test | S2 |
| MOB-02 | Navigation structure | Xon gen / Grace test | S2 |
| MOB-03 | Shared UI components | Xon gen / Grace test | S2 |
| MOB-04 | Home dashboard | Xon gen / Grace test | S2 |
| MOB-05 | Event detail screen | Xon gen / Grace test | S2 |
| MOB-06 | QR scanner screen | Xon gen / Grace test | S3 |
| MOB-07 | Rewards screens | Xon gen / Grace test | S3 |
| MOB-08 | Feedback & Q&A screens | Xon gen / Grace test | S3 |
| WEB-01 | Web project setup | Xon gen / Grace test | S2 |
| WEB-02 | Shared web components | Xon gen / Grace test | S2 |
| WEB-03 | Admin user management | Xon gen / Grace test | S3 |
| WEB-04 | Organization approval | Xon gen / Grace test | S3 |
| WEB-05 | Admin coupon management | Xon gen / Grace test | S4 |
| WEB-06 | Admin PIN verification | Xon gen / Grace test | S4 |
| WEB-07 | Admin audit & reports | Xon gen / Grace test | S4 |
| GAP-01 | Loading/error state audit | Grace | S5 |
| GAP-02 | API integration audit | Xon | S5 |
| GAP-03 | Documentation | All | Ongoing |
| GAP-04 | Presentation slides | All | S4-S5 |

Sprint Breakdown

Sprint 1 (7–27 May) — Foundation + Auth Backend

Xon (Infra):

INF-01 to INF-06 (scaffolding, DB, migrations, seeds, Git, error handler, rate limiter)

AUTH-01 to AUTH-06, AUTH-10 (registration, login, JWT, role guard, refresh, profile)

Nurain (Testing):

Test and verify AUTH-01 to AUTH-06, AUTH-10 on Expo Go

Register, login, JWT flow all working end-to-end

Vivian + Grace:

Assist Nurain with testing if time permits

Review database migrations and seed data

Deliverables: Express backend boots, DB has all 12 tables, auth APIs working, seed data populated.

Sprint 2 (28 May–17 Jun) — Auth Frontend + Events Backend

Xon (Code gen):

AUTH-07 to AUTH-09 (admin user mgmt, org registration, approval)

AUTH-M01 to AUTH-M04 (mobile auth screens)

EVT-01 to EVT-03 (event CRUD, search, registration)

EVT-M01, EVT-M02 (event browse, detail screens)

MOB-01 to MOB-05 (mobile project setup, navigation, UI kit, home, event detail)

Nurain (Testing):

Complete auth workflow end-to-end testing

Verify admin can manage users, approve organizations

Test all mobile auth screens on Expo Go

Vivian (Testing):

Start testing event CRUD, search, registration APIs

Verify event browse and detail screens on Expo Go

Grace (Testing):

Test mobile navigation structure, home dashboard, UI kit components

Set up web project shell

Deliverables: Full auth flow on mobile + web. Events API working. Mobile app with navigation skeleton.

Sprint 3 (18 Jun–8 Jul) — Events + QR + Rewards Backend

Xon (Code gen):

EVT-04 to EVT-10 (QR scan, attendance, feedback, Q&A, favorites, points)

EVT-M03 to EVT-M06 (scanner, feedback, event mgmt, Q&A screens)

REW-01 to REW-04, REW-08 (coupon CRUD, browse, redemption, PIN, quantity)

REW-M01 to REW-M04 (coupon screens)

MOB-06 to MOB-08 (scanner, rewards, feedback screens)

WEB-03, WEB-04 (admin user mgmt, org approval web pages)

Vivian (Testing):

Full events + QR + attendance + feedback workflow

Test QR scanner on Expo Go

Verify points awarded correctly

Grace (Testing):

Full rewards workflow: browse, redeem, PIN display

Test web admin pages

Nurain (Testing):

Verify org approval flow end-to-end (document upload → admin approve)

Test admin web user management

Deliverables: Events + QR scanning + attendance working. Rewards backend functional. Admin web portals partially built.

Sprint 4 (9–29 Jul) — Rewards Complete + Frontend Finish

Xon (Code gen):

REW-05 to REW-07 (PIN verification, audit log, auto-expire)

REW-W01 to REW-W03 (coupon mgmt, PIN verify, audit web pages)

WEB-05 to WEB-07 (admin web: coupon mgmt, PIN verify, audit reports)

Grace (Testing):

Complete rewards workflow including admin PIN verification and audit

Test all web portals

GAP-01, GAP-03 (state audit and documentation start)

Everyone:

Cross-test other workflows they haven't touched yet

Report edge cases and bugs

Deliverables: All 12 core tables working end-to-end. Mobile app complete. Admin web portal complete.

Sprint 5 (30 Jul–10 Aug) — Polish + Presentation

Everyone:

GAP-02 (API integration audit)

INF-07 (API consistency audit)

Bug fixes based on full-system testing

GAP-04 (Presentation slides and demo prep)

Live demo rehearsal

Q&A preparation

Final deliverable (10 August): Fully functional Volunteering Rewards App with:

Volunteer mobile: register, browse events, join, get scanned, earn points, redeem coupons

Organizer mobile: create events, manage attendance, scan QR, award points

Admin web: manage users, approve organizations, create coupons, verify PINs, view audit logs

Task Count Summary

| Member | Backend | Mobile | Web | Gap | Total Tasks | Test Checks |
| --- | --- | --- | --- | --- | --- | --- |
| Xon | INF-01 to INF-07 | — | — | GAP-02 | 8 core + code gen | — |
| Nurain | AUTH-01 to AUTH-10 | AUTH-M01 to AUTH-M04 | — | — | 14 | 14 |
| Vivian | EVT-01 to EVT-10 | EVT-M01 to EVT-M06 | — | — | 16 | 17 |
| Grace | REW-01 to REW-08 | REW-M01 to REW-M04 | REW-W01 to REW-W03, WEB-01 to WEB-07 | GAP-01, GAP-03, GAP-04 | 25 + 3 gap | 15 |
| Total | 35 | 18 | 10 | 4 | 67 | 46 |

Document version 2.1 — May 10, 2026