# Sprint 5 Schedule

Final Testing, Documentation & APK Build (V2)

Project: Volunteering Rewards App (C3000C)

Sprint: 29 Jun – 6 Jul 2026

Version: 2.0

Status: 🟡 Sprint In Progress — APK Build Complete, Testing Phase

# 1. Sprint Overview

Sprint 5 focuses on wrapping up all remaining work:

- ✅ Deployment already complete (done early)

- ✅ APK Build complete (app-release.apk generated, 83 MB)

- ⬜ APK Testing on real device (NEW)

- ⬜ Team testing tasks — security, integration, UAT

- ⬜ Documentation — report, slides, user manual

## Key Milestones

| Date | Milestone | Owner |
| --- | --- | --- |
| 29 Jun (Mon) | Sprint 5 kickoff — set up Android SDK | Xon |
| 29 Jun (Mon) | ✅ APK built successfully locally | Xon |
| 30 Jun–1 Jul | APK testing on device (Vivian + Nurain) | Vivian, Nurain |
| 1 Jul (Wed) | CI coverage & test DB | Xon |
| 2 Jul (Thu) | Security tests (Vivian), Integration tests (Grace), UAT-04/05/06 | Team |
| 3 Jul (Fri) | UAT-07/08; System tests; Sprint 5 close review | Team |
| 4 Jul (Sat) | 🎤 Dry-run presentation | All |
| 5 Jul (Sun) | Project report, slides, user manual due | Nurain |
| 6 Jul (Mon) | Final review & handover | All |

# 2. Task Assignments & Schedule

## Xon — CI/APK/Technical (Updated)

Note: APK build is now complete (6/6 tasks done). Remaining: CI and UAT.

| Day | Task | Jira | Est. Time | Status |
| --- | --- | --- | --- | --- |
| 29 Jun | Install JDK 17+ & Android SDK | KAN-148 | 35 min | ✅ Done |
| 29 Jun | Accept licenses, create local.properties | KAN-148 | 10 min | ✅ Done |
| 29 Jun | Pin AGP version & fix Gradle config | KAN-148 | 10 min | ✅ Done |
| 29 Jun | First local APK build attempt | KAN-149 | 30 min | ✅ Done |
| 29 Jun | Fix build errors (10 issues resolved) | KAN-149 | 60 min | ✅ Done |
| 29 Jun | app-release.apk generated (83 MB) | KAN-149 | — | ✅ Done |
| 30 Jun | Tag v1.1.0 release on GitHub | KAN-149 | 10 min | ⬜ |
| 1 Jul | CI coverage reporting in ci.yml | KAN-150 | 30 min | ⬜ |
| 1 Jul | PostgreSQL service container for CI tests | KAN-151 | 30 min | ⬜ |
| 1 Jul | UAT-01/02/03: Admin scenarios | KAN-140 | 40 min | ⬜ |
| 1 Jul | Upload APK to GitHub for team download | — | 10 min | ⬜ |

## Vivian — Security Tests, UAT & APK Testing (NEW)

NEW: APK testing tasks assigned (APK-TEST-01/02). See Section 3 for details.

| Day | Task | Jira | Est. Time | Deliverable |
| --- | --- | --- | --- | --- |
| 2 Jul (Thu) | Security tests: 12 cases (JWT, SQLi, XSS, rate limiting, role guards) | KAN-152 | 3 hr | Security test report |
| 2 Jul (Thu) | UAT-04: Volunteer Browses & Joins Events | KAN-140 | 20 min | UAT result |
| 2 Jul (Thu) | APK-TEST-01: Install APK on Android device + verify app launch | NEW | 30 min | Test result |
| 2 Jul (Thu) | APK-TEST-02: Test home screen, navigation, events flow | NEW | 30 min | Test result |
| 3 Jul (Fri) | UAT-07: Organiser Manages Events (with Nurain) | KAN-140 | 20 min | UAT result |
| 3 Jul (Fri) | Retest any bugs found | — | 30 min | Bug fixes verified |

## Grace — Integration Tests & UAT

| Day | Task | Jira | Est. Time | Status |
| --- | --- | --- | --- | --- |
| ✅ Done | Integration tests: 34 cases — already completed | KAN-138 | — | ✅ Done |
| 2 Jul | UAT-05: Volunteer Redeems Rewards | KAN-140 | 15 min | ⬜ |
| 2 Jul | UAT-06: Merchant Verifies PIN | KAN-140 | 15 min | ⬜ |

## Nurain — Documentation, UAT & APK Testing (NEW)

NEW: APK testing tasks assigned (APK-TEST-03/04). See Section 3 for details.

| Day | Task | Jira | Est. Time | Deliverable |
| --- | --- | --- | --- | --- |
| 1 Jul (Wed) | Start project report from C300 Report Template | KAN-141 | 3 hr | Draft report |
| 2 Jul (Thu) | Continue report + work on presentation slides | KAN-141/142 | 3 hr | Report v2 + slides |
| 2 Jul (Thu) | APK-TEST-03: Test login/auth, profile, settings on APK | NEW | 30 min | Test result |
| 2 Jul (Thu) | APK-TEST-04: Test performance, stability, rotation, crash test | NEW | 30 min | Test result |
| 3 Jul (Fri) | UAT-08: Role-Based Access Control | KAN-140 | 10 min | UAT result |
| 4 Jul (Sat) | Finalize slides for dry-run | KAN-142 | 2 hr | Slides v1 |
| 5 Jul (Sun) | Complete user manual | KAN-143 | 2 hr | User manual v1 |

## Whole Team — System Tests & Dry-Run

| Day | Task | Owner | Est. Time |
| --- | --- | --- | --- |
| ✅ Done | System tests: 6 E2E workflows — already completed | Xon | ✅ Done |
| 3 Jul | Retest any E2E issues if needed | All | 1 hr |
| 4 Jul | 🎤 Dry-run presentation | All | 2 hr |
| 6 Jul | Sprint close — incorporate dry-run feedback | All | 1 hr |

# 3. APK Testing Tasks — Detailed Breakdown (NEW)

The native Android APK has been successfully built (app-release.apk, 83 MB). It now needs to be tested on real Android devices.

APK location:

frontend/mobile_app/android/app/build/outputs/apk/release/app-release.apk

Full testing instructions are documented in: docs/apk-testing-guide.md

| ID | Test Area | Tester | Est. Time | Reference |
| --- | --- | --- | --- | --- |
| APK-TEST-01 | Install APK, verify app launch & splash screen | Vivian | 30 min | §3–4.1 in testing guide |
| APK-TEST-02 | Home screen, navigation tabs, events flow | Vivian | 30 min | §4.2–4.4 in testing guide |
| APK-TEST-03 | Login/auth, profile, settings | Nurain | 30 min | §4.5–4.6 in testing guide |
| APK-TEST-04 | Performance, stability, rotation, crash test | Nurain | 30 min | §4.7 in testing guide |

If crashes or bugs are found during APK testing, report with reproduction steps + logcat output (see apk-testing-guide.md §5). Report to Xon for fixes.

# 4. UAT & APK Testing Assignment Summary

| ID | Scenario | Owner | Portal | Est. Time |
| --- | --- | --- | --- | --- |
| UAT-01 | Admin Onboards Organiser | Xon | Admin | 15 min |
| UAT-02 | Admin Manages Coupons | Xon | Admin | 15 min |
| UAT-03 | Admin Configures Rewards | Xon | Admin | 10 min |
| UAT-04 | Volunteer Browses & Joins Events | Vivian | Volunteer PWA | 20 min |
| UAT-05 | Volunteer Redeems Rewards | Grace | Volunteer PWA | 15 min |
| UAT-06 | Merchant Verifies PIN | Grace | Merchant | 15 min |
| UAT-07 | Organiser Manages Events | Vivian / Nurain | Organiser | 20 min |
| UAT-08 | Role-Based Access Control | Nurain | All portals | 10 min |
| APK-TEST-01 | Install & launch APK | Vivian | Android | 30 min |
| APK-TEST-02 | Home & events flow on APK | Vivian | Android | 30 min |
| APK-TEST-03 | Auth & profile on APK | Nurain | Android | 30 min |
| APK-TEST-04 | Performance & stability on APK | Nurain | Android | 30 min |

# 5. Risk Table

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| APK crashes on real device (runtime errors) | Medium | Medium | Capture logcat, fix in next iteration; PWA is primary delivery |
| Team members don't complete UAT on time | Medium | Medium | Xon covers any unassigned UAT as backup |
| APK testing reveals bugs requiring code fixes | Medium | Medium | Timebox fixes to 1 day; PWA is fallback |
| Dry-run reveals major presentation gaps | Low | Medium | Schedule 2 hr buffer on 5 Jul for fixes |

# 6. Current Progress Snapshot

| Area | Completion | Owner |
| --- | --- | --- |
| ✅ Backend API | 100% | Xon |
| ✅ All Portals Deployed | 100% | Xon |
| ✅ PWA Live | 100% | Xon |
| ✅ Xon's Tasks | 100% (24/24) | Xon |
| ✅ Native APK Build | 100% (8/8) — DONE | Xon |
| ⬜ APK Testing on Device | 0% (0/4) — NEW | Vivian, Nurain |
| ⬜ CI Coverage & Test DB | 0% (0/2) | Xon |
| ⬜ Security Tests | 0% (0/12) | Vivian |
| ✅ Integration Tests | 100% (34/34) — done | Grace |
| ✅ System Tests (E2E) | 100% (6/6) — done | Xon |
| ⬜ UAT Scenarios | 0% (0/8) | Team |
| ⬜ Project Report | 0% | Nurain |
| ⬜ Presentation Slides | 0% | Nurain |
| ⬜ User Manual | 0% | Nurain |
| 🏁 Final Delivery | 0% | All |

# 7. Jira Issue Reference — Sprint 5

| Key | Task | Owner | Status |
| --- | --- | --- | --- |
| KAN-148 | APK-BUILD-v1: Install JDK 17+ & Android SDK | Xon Loke | ✅ Done |
| KAN-149 | APK-BUILD-v2: Build native APK locally | Xon Loke | ✅ Done |
| KAN-150 | CI-COVERAGE-v1: Test coverage reporting | Xon Loke | To Do |
| KAN-151 | CI-TESTDB-v1: PostgreSQL test database in CI | Xon Loke | To Do |
| KAN-122 | MOBILE-EAS-BLOCKED: Expo EAS build failure | Xon Loke | To Do |
| KAN-140 | User Acceptance Tests (8 scenarios) | Xon Loke | To Do |
| KAN-141 | Project report from C300 Report Template | Nur Ain | To Do |
| KAN-142 | Presentation slides | Nur Ain | To Do |
| KAN-143 | User manual — step-by-step for all roles | Nur Ain | To Do |
| KAN-144 | Dry-run presentation + team feedback | Xon Loke | To Do |
| KAN-145 | Final delivery | Xon Loke | To Do |
| KAN-152 | SEC-TESTS-v1: Security tests (12 cases) | Vivian Koh | To Do |
| KAN-NEW | APK testing on Android device (4 tasks) | Vivian / Nurain | To Do — NEW |

Board: https://fengshui0011.atlassian.net/jira/software/projects/KAN/boards/2

End of Sprint 5 Schedule v2.0